## ✋Start here
👋 Tab 1: Start here | 📢 Tab 2: Updates | 👩‍💻 Tab 3: Team | 📋 Tab 4: App assessment | ✅ Tab 5: Pre-migration checklist | 📖 Tab 6: Migration runbook | 🧪 Tab 7: UAT test cases | ☑️Tab 8: Post-migration checklist
To get started, make a copy of this read-only spreadsheet and begin adding information about your team’s migration.
Cloud migrations require partnership among teams at your own organization, Atlassian, and the Solution Partner organization - if you’re planning to work with one. Use this spreadsheet to keep track of project updates, prepare for your migration and communicate with your migration team. We've populated some of the templates with example data and best practices. Keep in mind that some steps may not apply to your migration and that there may be steps you’ll need to add based on your migration. | Use this tab to keep track of topics and conversations that require repeated followup - anything that doesn't make sense to track in your migration support ticket, if you have one. | Add all team members who will be working on the migration, including individuals within your organization, at Atlassian, or at the Solution Partner organization. | Assessing which apps you need to migrate, their Cloud availability and feature set, and how to migrate the data is one of the most critical migration planning activities. Use this tab to keep track of your app assessment and start planning for migration. | Run through this checklist to prepare your Server and Cloud instances for migration and to reduce the risk of data migration issues. | Use this template to prepare your migration runbook – your step-by-step plan for a flawless migration. | Use this a starting point for your User Acceptance Testing plan. | Use this checklist as a starting point to ensure that everything that should have been migrated did get migrated during the production migration.

## 📢 Updates
Task or topic | Description | Status | Priority | Status Update | Associated Ticket | Assigned to | Start Date | End Date
(Example task - you can delete this row) Change management | Changes need to be reviewed in advance to limit what is introduced and control product release. | 1. To do | 2. Medium | Discussed the Cloud Enterprise Plan and upcoming capabilities for Release Tracks on May 19th. Also shared the Jira, Confluence and Cloud Platform roadmaps with team so they can see what's coming. They will discuss with their EA and SE next week. | N/A | Name (CMM) | 2020-04-22

## 👩‍💻 Team
Name | Role | Company | Key tasks | Email
(Example) Cecilia Davidson | Ops Engineering | Acme. co | Migration testing and user communications | cdavidson@acmeco.com

## 📋App assessment
Product | App name | Essential? | Cloud version | App feature parity | Migration path available? | Marketplace link | Users | # of users | Cloud features available? | Data migration required? | Cloud alternatives | Cloud alternatives | Notes
Which product is this app for? | What is the name on Marketplace, or internal name for custom apps? | Is this app's functionality critical to have in cloud? | Does the app have a cloud version? | Add the URL to Marketplace Vendor documentation describing feature differences between server and cloud versions of this app (if available) | Note whether the app has an automated migration path available. Alternatively, add the URL to Marketplace Vendor documentation describing the server to cloud migration path (if available) | Add the Atlassian Marketplace URL for this app. | Which teams or people use the app? | How many people are using the app? This can be a best guess, or use the cloud migration assistants to determine usage. | Does functionality in the cloud product replace the need for this app? | Do you need to migrate data associated with this app to cloud? | Does the app have cloud alternatives? | What are the alternatives?
💡 See how to pull this data directly from your server instance with the Coud Migration Assistants

## ✅Pre-migration checklist
| Priority | Status | Responsible | Comments
💡For the full pre-migration checklist, refer to the documentation
Jira Pre-Migration Checklist
Confluence Pre-Migration Checklist
MIGRATION METHOD: CONFLUENCE CLOUD MIGRATION ASSISTANT
Confirm your migration method | Mandatory
Confirm your user migration plan | Mandatory
Ensure you won’t exceed your cloud user limit | Mandatory
Ensure you have the right permissions | Mandatory
Check your Confluence Server version | Mandatory
Fix any app or add-on email addresses | Mandatory
Fix any duplicate email addresses | Mandatory
Fix any duplicate usernames | Mandatory
Rename restricted groups | Mandatory
Update your firewall allowance rules | Mandatory
Determine how you’ll migrate apps | Mandatory
Check your public access settings | Mandatory
Check your Heap Allocation | Mandatory
Back up your cloud site | Recommended
Run a test migration | Recommended
Notify support of your migration plan | Recommended
MIGRATION METHOD: CONFLUENCE CLOUD SPACE BY SPACE (XML) IMPORT
Confirm your migration method | Mandatory
Confirm your user migration plan | Mandatory
Ensure you have the right permissions | Mandatory
Determine how you’ll migrate apps | Mandatory
Determine how you’ll migrate apps | Mandatory
Check your XML structure | Mandatory
Ensure you have the right type of export | Mandatory
Check for duplicate space keys | Mandatory
Check your Heap Allocation | Mandatory
Back up your cloud site | Mandatory
Run a test migration | Mandatory
Notify support of your migration plan | Mandatory
MIGRATION METHOD: JIRA CLOUD MIGRATION ASSISTANT
Confirm your migration method | Mandatory
Create a user migration plan | Mandatory
Check your Jira Server version | Mandatory
Fix any duplicate email addresses | Mandatory
Make sure you have the right permissions | Mandatory
Check for conflicts with group names | Mandatory
Update your firewall allowance rules | Mandatory
Determine how you’ll migrate apps | Mandatory
Check your public access settings | Mandatory
Review your server setup | Mandatory
Check your server timezone (if merging cloud sites) | Mandatory
Fix any duplicate shared configuration names | Recommended
Check you won't exceed storage limits | Recommended
Prepare your server instance | Recommended
Prepare your cloud site | Recommended
Back up your cloud site | Recommended
Run a test migration | Recommended
Notify support of your migration plan | Recommended
MIGRATION METHOD: JIRA CLOUD SITE (XML) IMPORT
Confirm your migration method | Mandatory
Check your Jira Server version | Mandatory
Check your XML file is valid | Mandatory
Check your XML file structure | Mandatory
Check for failed upgrade tasks | Mandatory
Check for duplicate and invalid user emails | Mandatory
Check for invalid or unhandled characters | Mandatory
Fix any duplicate workflows | Mandatory
Fix any duplicate clustered jobs | Mandatory
Check the length of your attachment filenames | Mandatory
Check your public access settings | Mandatory
Check the size of your attachments | Recommended
Check for orphan data | Recommended
Check you won't exceed storage limits | Recommended
Back up your cloud site | Recommended
Run a test migration | Recommended
Notify support of your migration plan | Recommended

## 📖Migration runbook
Task | Timeline | Product | Method | Date | Start time | Duration (minutes) | End time | Priority | Responsible | Status | Notes
PRE-TEST MIGRATION
Develop UAT plan | Pre-test migration | Both | All |  |  |  |  | Mandatory | Customer |  | Customer to start creating UAT logistics (e.g. who, when, how)
Send UAT plan to UAT users | Pre-test migration | Both | All |  |  |  |  | Mandatory | Customer |  | Customer to notify users of the plan to perform UAT
Check for app link dependencies for cloud to server linking for non-cloud Atlassian products (hybrid deployments) | Pre-test migration | Both | All |  |  |  |  | Mandatory | Customer |  | Link to documentation
Audit link requirements to see what needs to be fixed post-production migration | Pre-test migration | Both | All |  |  |  |  | Mandatory | Customer
Ensure there's an app migration strategy defined | Pre-test migration | Both | All |  |  |  |  | Mandatory | Atlassian |  | Link to documentation: Develop an app migration strategy, open vendor tickets, etc.
Ensure there's a data migration strategy defined | Pre-test migration | Both | All |  |  |  |  | Mandatory | Atlassian |  | Link to documentation: Develop a data migration strategy
Ensure there's a user migration strategy defined | Pre-test migration | Both | All |  |  |  |  | Mandatory | Atlassian |  | Link to documentation
Ensure there's an attachment migration strategy defined | Pre-test migration | Jira | Site Import |  |  |  |  | Recommended | Atlassian |  | Link to documentation
If you are merging Jira instances and you need to take a phased migration approach via JCMA, please ensure you put a freeze on shared entities in server and cloud to prevent configuration drift | Pre-test migration | Jira | Migration Assitant |  |  |  |  | Mandatory | Customer |  | Link to documentation
Identify Confluence macros in server/DC to see what needs to be tested | Pre-test migration | Confluence | All |  |  |  |  | Mandatory | Customer |  | Link to documentation
Set up a test site/ensure current site has an extended trial | Pre-test migration | Both | All |  |  |  |  | Mandatory | Customer |  | Link to documentation
Complete pre-migration checklist | Pre-test migration | Jira | All |  |  |  |  | Mandatory | Atlassian/Customer |  | Link to documentation
Complete pre-migration checklist | Pre-test migration | Confluence | All |  |  |  |  | Mandatory | Atlassian/Customer |  | Link to documentation
TEST MIGRATION
Feature Flag Preparation | Test migration | Both | Site Import |  |  |  |  | Mandatory | Atlassian |  | Atlassian support to review feature flags required for this migration. Please add a line item for the feature flags used for the migration (if required)
Execute user migration strategy | Test migration | Both | All |  |  |  |  | Mandatory | Atlassian |  | Link to documentation
Migrate Users and Groups/Memberships | Test migration | Jira | Migration Assitant |  |  |  |  | Recommended | Atlassian
Clean up user accounts (all emails valid and unique) in Server | Test migration | Both | Migration Assitant |  |  |  |  | Mandatory | Customer
Execute attachment migration strategy | Test migration | Jira | Site Import |  |  |  |  | Recommended | Atlassian/Customer |  | Link to documentation
Perform Migration | Test migration | Both | All |  |  |  |  | Mandatory | Atlassian/Customer |  | Link to documentation
Ensure the customer hardware is capable of performing adequately | Test migration | Both | Migration Assitant |  |  |  |  | Mandatory | Customer |  | Link to documentation - Take a thread and CPU dump WHILE the migration is happening so Support can confirm resourcing
Placeholder - fill in tasks specific to this migration | Test migration |  | All
Placeholder - fill in tasks specific to this migration | Test migration |  | All
Install Apps | Test migration | Both | All |  |  |  |  | Mandatory | Customer
Post-Migration Fixes | Test migration | Both | All |  |  |  |  | Recommended | Customer |  | Use the following documentation to learn more about product links and how to ensure they are working post-migration. -What are product links? -Supported products and types of links -Update product links -Examples and use cases for updating product links -Check the status and results -Updating URL links after a successful migration
Update links in Confluence to point to new Confluence address | Test migration | Confluence | All |  |  |  |  | Recommended | Customer
Update links in Confluence to point to new Jira address | Test migration | Confluence | All |  |  |  |  | Recommended | Customer
Update links in Jira to point to new Jira address | Test migration | Jira | All |  |  |  |  | Recommended | Customer
Update links in Jira to point to new Confluence address | Test migration | Jira | All |  |  |  |  | Recommended | Customer
Test macros in cloud to identify if there are broken macros | Test migration | Confluence | All |  |  |  |  | Mandatory | Customer |  | If there are broken macros, work with support to see if there are ways to resolve it. If the macro is from a third party app, will need to work with vendor to check for resolution
Run Jira Macro Repair | Test migration | Confluence | All |  |  |  |  | Mandatory | Customer
Check Anonymous Access in Cloud | Test migration | Jira | All |  |  |  |  | Recommended | Atlassian/Customer
Enable SSO/User Provisioning | Test migration | Both | All |  |  |  |  | Optional | Atlassian/Customer
Send communication to start UAT | Test migration | Both | All |  |  |  |  | Recommended | Customer |  | Make sure to test all portions of the application, including Jira Service Desk, customer logins, look and feel, etc.
PRE-PROD MIGRATION
Ensure CMA version parity by preventing forced upgrades | Pre-prod migration | Both | Migration Assitant |  |  |  |  | Mandatory | Atlassian/Customer
Touchpoint with Atlassian: review runbook | Pre-prod migration | Both | All |  |  |  |  | Mandatory | Atlassian/Customer
Ensure prod site has an extended trial/license validation | Pre-prod migration | Both | All |  |  |  |  | Mandatory | Atlassian/Customer |  | Link to documentation - Ensure the instance has an ECTL license or has changed the Free License at least "Standard" through "Manage Subscriptions" at site.atlassian.net/admin
If cutover date available, ensure end users are alerted ahead of time of migration | Pre-prod migration | Both | All |  |  |  |  | Mandatory | Atlassian/Customer
Develop post-migration support plan for admins and users | Pre-prod migration | Both | All |  |  |  |  | Recommended | Customer |  | Customer to discuss internally on the support logistics
Complete pre-migration checklist | Pre-prod migration | Jira | All |  |  |  |  | Mandatory | Atlassian/Customer |  | Link to documentation
Complete pre-migration checklist | Pre-prod migration | Confluence | All |  |  |  |  | Mandatory | Atlassian/Customer |  | Link to documentation
Review UAT plan | Pre-prod migration | Both | All |  |  |  |  | Mandatory | Customer
Send UAT plan to UAT users | Pre-prod migration | Both | All |  |  |  |  | Mandatory | Customer
Add announcement banner outlining changes are coming | Pre-prod migration | Jira | All |  |  |  |  | Recommended | Customer |  | Link to documentation
Add announcement banner outlining changes are coming | Pre-prod migration | Confluence | All |  |  |  |  | Recommended | Customer |  | Link to documentation
Cease granting licenses to users | Pre-prod migration | Both | All |  |  |  |  | Mandatory | Customer |  | Stop granting licenses on the destination to prevent drift in users
Pause LDAP sync job | Pre-prod migration | Both | All |  |  |  |  | Recommended | Customer
Migrate Users and Groups/Memberships | Pre-prod migration | Jira | Site Import |  |  |  |  | Recommended | Atlassian/Customer |  | Recommended to get a CSV export a day before production run
Verify that all LDAP users have Atlassian account IDs | Pre-prod migration | Jira | Site Import |  |  |  |  | Recommended | Atlassian
Unpause LDAP sync job | Pre-prod migration | Both | All |  |  |  |  | Recommended | Customer
Update announcement banner stating when site will be read-only | Pre-prod migration | Jira | All |  |  |  |  | Mandatory | Customer |  | Link to documentation
Update announcement banner stating when site will be read-only | Pre-prod migration | Confluence | All |  |  |  |  | Mandatory | Customer |  | Link to documentation
Ensure you are using the same version of CMA's that was tested with (Support to provide steps if forced upgrade is prompted) | Pre-prod migration | Both | Migration Assitant |  |  |  |  | Mandatory | Atlassian
Feature Flag Preparation | Pre-prod migration | Jira | Site Import |  |  |  |  | Mandatory | Atlassian
PROD MIGRATION
Set server to read-only | Prod-migration | Jira | All |  |  |  |  | Recommended | Atlassian/Customer |  | Provide load balancer, proxy or permission scheme options
Set server to read-only | Prod-migration | Confluence | All |  |  |  |  | Recommended | Atlassian/Customer |  | Provide load balancer, proxy or permission scheme options
Update announcement banner stating site is now read-only | Prod-migration | Jira | All |  |  |  |  | Recommended | Customer |  | Link to documentation
Update announcement banner stating site is now read-only | Prod-migration | Confluence | All |  |  |  |  | Recommended | Customer |  | Link to documentation
Perform Migration | Prod-migration | Both | All |  |  |  |  | Mandatory | Atlassian/Customer |  | Link to documentation
Placeholder - fill in tasks specific to this migration | Prod-migration |  | All
Placeholder | Prod-migration |  | All
Post-Migration Fixes | Prod-migration | Both | All |  |  |  |  | Recommended | Customer
Update links in Confluence to point to new Confluence address | Prod-migration | Confluence | All |  |  |  |  | Recommended | Customer |  | Product links are links to individual entities (for example, Jira issues, Confluence pages) in other Atlassian products or in the same product.
Update links in Confluence to point to new Jira address | Prod-migration | Confluence | All |  |  |  |  | Recommended | Customer |  | Supported products and types of links | Examples and use cases for updating product links
Update links in Jira to point to new Jira address | Prod-migration | Jira | All |  |  |  |  | Recommended | Customer |  | Update product links | New cloud instance URL links
Update links in Jira to point to new Confluence address | Prod-migration | Jira | All |  |  |  |  | Recommended | Customer |  | Check the status and results of updating product links
Run Jira Macro Repair | Prod-migration | Confluence | All |  |  |  |  | Mandatory | Customer
Check Anonymous Access in Cloud | Prod-migration | Jira | All |  |  |  |  | Recommended | Atlassian/Customer |  | Link to documentation
Check Anonymous Access in Cloud | Prod-migration | Confluence | All |  |  |  |  | Recommended | Atlassian/Customer |  | Link to documentation
Update projects with project avatars | Prod-migration | Jira | Site Import |  |  |  |  | Recommended | Atlassian
Complete the UAT | Prod-migration | Both | All |  |  |  |  | Recommended | Customer
Decision point: Go/No go | Prod-migration | Both | All |  |  |  |  | Mandatory | Customer
Check-in with Atlassian | Prod-migration | Both | All |  |  |  |  | Mandatory | Customer
ROLLBACK PLAN
Update announcement banner stating migration is a No-Go and remove read-only | Rollback plan | Jira | All |  |  |  |  | Recommended | Customer |  | Link to documentation
Update announcement banner stating migration is a No-Go and remove read-only | Rollback plan | Confluence | All |  |  |  |  | Recommended | Customer |  | Link to documentation
Remove server from read-only | Rollback plan | Both | All |  |  |  |  | Recommended | Customer
Remove partially migrated projects in cloud | Rollback plan | Jira | Migration Assitant |  |  |  |  | Conditional | Customer |  | Leave the data if investigation is needed to identify cause of migration failure
Remove partially migrated spaces in cloud | Rollback plan | Confluence | Migration Assitant |  |  |  |  | Conditional | Customer |  | Leave the data if investigation is needed to identify cause of migration failure
POST-PROD MIGRATION
Set up SSO | Post-prod migration | Both | All |  |  |  |  | Conditional | Customer
Set up SCIM user provisioning | Post-prod migration | Both | All |  |  |  |  | Conditional | Customer
Triage and fix issues | Post-prod migration | Both | All |  |  |  |  | Conditional | Atlassian/Customer
Check-in with Atlassian | Post-prod migration | Both | All |  |  |  |  | Mandatory | Customer

## 📖Migration runbook - (For Atla (hidden)
ID # | Task | Timeline | Product | Method | Date | Start time | Duration (minutes) | End time | Priority | Responsible | Status | Notes
PRE-TEST MIGRATION
| Develop UAT plan | Pre-test migration | Both | All |  |  |  |  | Mandatory | Customer |  | Customer to start creating UAT logistics (e.g. who, when, how)
| Send UAT plan to UAT users | Pre-test migration | Both | All |  |  |  |  | Mandatory | Customer |  | Customer to notify users of the plan to perform UAT
| Check for app link dependencies for cloud to server linking for non-cloud Atlassian products (hybrid deployments) | Pre-test migration | Both | All |  |  |  |  | Mandatory | Customer |  | Link to documentation
| Audit link requirements to see what needs to be fixed post-production migration | Pre-test migration | Both | All |  |  |  |  | Mandatory | Customer
| Ensure there's an app migration strategy defined | Pre-test migration | Both | All |  |  |  |  | Mandatory | Atlassian |  | Link to documentation: Develop an app migration strategy, open vendor tickets, etc.
| Ensure there's a data migration strategy defined | Pre-test migration | Both | All |  |  |  |  | Mandatory | Atlassian |  | Link to documentation: Develop a data migration strategy
| Ensure there's a user migration strategy defined | Pre-test migration | Both | All |  |  |  |  | Mandatory | Atlassian |  | Link to documentation
| Ensure there's an attachment migration strategy defined | Pre-test migration | Jira | Site Import |  |  |  |  | Recommended | Atlassian |  | Link to documentation
| If you are merging Jira instances and you need to take a phased migration approach via JCMA, please ensure you put a freeze on shared entities in server and cloud to prevent configuration drift | Pre-test migration | Jira | Migration Assitant |  |  |  |  | Mandatory | Customer |  | Link to documentation
| Identify Confluence macros in server/DC to see what needs to be tested | Pre-test migration | Confluence | All |  |  |  |  | Mandatory | Customer |  | Link to documentation
| Set up a test site/ensure current site has an extended trial | Pre-test migration | Both | All |  |  |  |  | Mandatory | Customer |  | Link to documentation
| Complete pre-migration checklist | Pre-test migration | Jira | All |  |  |  |  | Mandatory | Atlassian/Customer |  | Link to documentation
| Complete pre-migration checklist | Pre-test migration | Confluence | All |  |  |  |  | Mandatory | Atlassian/Customer |  | Link to documentation
TEST MIGRATION
| Feature Flag/Instance Preparation | Test migration | Both | Site Import |  |  |  |  | Conditional | Atlassian |  | Link to Documentation - Make sure you add needed feature flags to the instance, such as e-mail limitation and re-indexing post import ones.
| Add Tenant to Segment for FFs | Test migration | Jira | Site Import |  |  |  |  | Mandatory | Atlassian |  | Link to documentation (Atlassian internal)
| Dedicated RDS process | Test migration | Jira | All |  |  |  |  | Recommended | Atlassian |  | Link to documentation (Atlassian internal)
| Allow User Script to Run (user import script will fail if this is not enabled) | Test migration | Both | Site Import |  |  |  |  | Conditional | Atlassian |  | Link to documentation (Atlassian internal) There is a new flag to allow user import script to continue to work.
| PENDING - Disable JCMA redirect Validation - To allow site imports without redirecting to JCMA | Test migration | [9 empty] | https://app.launchdarkly.com/jira/production/features/val-718-enable-jcma-redirect-validation
| PENDING - 10K Migrators with Old issue View | Test migration | Jira | All |  |  |  |  | Conditional | Atlassian |  | https://app.launchdarkly.com/jira/production/segments/10k-migrators-old-iv/targeting
| Execute user migration strategy | Test migration | Both | All |  |  |  |  | Mandatory | Atlassian |  | Link to documentation
| Migrate Users and Groups/Memberships | Test migration | Jira | Site Import |  |  |  |  | Recommended | Atlassian |  | Link to documentation (Atlassian internal)
| Clean up user accounts (all emails valid and unique) in Server | Test migration | Both | Migration Assitant |  |  |  |  | Mandatory | Customer
| Execute attachment migration strategy | Test migration | Jira | Site Import |  |  |  |  | Recommended | Atlassian/Customer |  | Link to documentation
| Perform Migration | Test migration | Both | All |  |  |  |  | Mandatory | Atlassian/Customer |  | Link to documentation
| Placeholder - fill in tasks specific to this migration | Test migration |  | All
| Placeholder - fill in tasks specific to this migration | Test migration |  | All
| Install Apps | Test migration | Both | All |  |  |  |  | Mandatory | Customer
| Post-Migration Fixes | Test migration | Both | All |  |  |  |  | Mandatory | Atlassian
| Update links in Confluence to point to new Confluence address | Test migration | Confluence | All |  |  |  |  | Mandatory | Atlassian
| Update links in Confluence to point to new Jira address | Test migration | Confluence | All |  |  |  |  | Mandatory | Atlassian
| Update links in Jira to point to new Jira address | Test migration | Jira | All |  |  |  |  | Mandatory | Atlassian
| Update links in Jira to point to new Confluence address | Test migration | Jira | All |  |  |  |  | Mandatory | Atlassian
| Test macros in cloud to identify if there are broken macros | Test migration | Confluence | All |  |  |  |  | Mandatory | Customer |  | If there are broken macros, work with support to see if there are ways to resolve it. If the macro is from a third party app, will need to work with vendor to check for resolution
| Run Jira Macro Repair | Test migration | Confluence | All |  |  |  |  | Mandatory | Customer
| Check Anonymous Access in Cloud | Test migration | Jira | All |  |  |  |  | Recommended | Atlassian/Customer
| Enable SSO/User Provisioning | Test migration | Both | All |  |  |  |  | Optional | Atlassian/Customer
| Send comms to start UAT | Test migration | Both | All |  |  |  |  | Recommended | Customer |  | Make sure to test all portions of the application, including Jira Service Desk, customer logins, look and feel, etc.
| Enable indexing on cloud if disabled in the beginning of test | Test migration | Jira | Site Import |  |  |  |  | Recommended | Atlassian |  | Link to documentation (Atlassian internal)
PRE-PROD MIGRATION
| Ensure CMA version parity by preventing forced upgrades | Pre-prod migration | Both | Migration Assitant |  |  |  |  | Mandatory | Atlassian/Customer |  | Link to documentation and Link to documentation
| Touchpoint with Atlassian: review runbook | Pre-prod migration | Both | All |  |  |  |  | Mandatory | Atlassian/Customer
| Ensure prod site has an extended trial/license validation | Pre-prod migration | Both | All |  |  |  |  | Mandatory | Atlassian/Customer |  | Link to documentation - Ensure the instance has an ECTL license or has changed the Free License at least "Standard" through "Manage Subscriptions" at site.atlassian.net/admin
| If cutover date available, ensure end users are alerted ahead of time of migration | Pre-prod migration | Both | All |  |  |  |  | Mandatory | Atlassian/Customer
| Develop post-migration support plan for admins and users | Pre-prod migration | Both | All |  |  |  |  | Recommended | Customer |  | Customer to discuss internally on the support logistics
| Complete pre-migration checklist | Pre-prod migration | Jira | All |  |  |  |  | Mandatory | Atlassian/Customer |  | Link to documentation
| Complete pre-migration checklist | Pre-prod migration | Confluence | All |  |  |  |  | Mandatory | Atlassian/Customer |  | Link to documentation
| Review UAT plan | Pre-prod migration | Both | All |  |  |  |  | Mandatory | Customer
| Send UAT plan to UAT users | Pre-prod migration | Both | All |  |  |  |  | Mandatory | Customer
| Add announcement banner outlining changes are coming | Pre-prod migration | Jira | All |  |  |  |  | Recommended | Customer |  | Link to documentation
| Add announcement banner outlining changes are coming | Pre-prod migration | Confluence | All |  |  |  |  | Recommended | Customer |  | Link to documentation
| Cease granting licenses to users | Pre-prod migration | Both | All |  |  |  |  | Mandatory | Customer |  | Stop granting licenses on the destination to prevent drift in users
| Pause LDAP sync job | Pre-prod migration | Both | All |  |  |  |  | Recommended | Customer
| Migrate Users and Groups/Memberships | Pre-prod migration | Jira | Site Import |  |  |  |  | Recommended | Atlassian/Customer |  | Link to documentation (Atlassian internal) - recommended to get a CSV export a day before production run
| Verify that all LDAP users have Atlassian account IDs | Pre-prod migration | Jira | Site Import |  |  |  |  | Recommended | Atlassian
| Unpause LDAP sync job | Pre-prod migration | Both | All |  |  |  |  | Recommended | Customer
| Update announcement banner stating when site will be read-only | Pre-prod migration | Jira | All |  |  |  |  | Mandatory | Customer |  | Link to documentation
| Update announcement banner stating when site will be read-only | Pre-prod migration | Confluence | All |  |  |  |  | Mandatory | Customer |  | Link to documentation
| Feature Flag Preparation | Pre-prod migration | Jira | Site Import |  |  |  |  | Conditional | Customer |  | Link to Documentation - Make sure you add needed feature flags to the instance, such as e-mail limitation and re-indexing post import ones.
| Compare feature flags between test and prod | Pre-prod migration | Jira | Site Import |  |  |  |  | Mandatory | Atlassian |  | Link to documentation (Atlassian internal)
| Dedicated RDS process - check if changes needed | Pre-prod migration | Jira | All |  |  |  |  | Recommended | Atlassian |  | Link to documentation (Atlassian internal)
| Ensure CMA is running same version as test | Pre-prod migration | Both | All |  |  |  |  | Mandatory | Atlassian |  | Link to documentation - ensure to compare test and production instance FFs via https://go.atlassian.com/ff-diff
PROD MIGRATION
| Set server to read-only | Prod-migration | Jira | All |  |  |  |  | Recommended | Atlassian/Customer |  | Provide load balancer, proxy or permission scheme options
| Set server to read-only | Prod-migration | Confluence | All |  |  |  |  | Recommended | Atlassian/Customer |  | Provide load balancer, proxy or permission scheme options
| Update announcement banner stating site is now read-only | Prod-migration | Jira | All |  |  |  |  | Recommended | Customer |  | Link to documentation
| Update announcement banner stating site is now read-only | Prod-migration | Confluence | All |  |  |  |  | Recommended | Customer |  | Link to documentation
| Perform Migration | Prod-migration | Both | All |  |  |  |  | Mandatory | Atlassian/Customer |  | Link to documentation
| Placeholder - fill in tasks specific to this migration | Prod-migration |  | All
| Placeholder | Prod-migration |  | All
| Post-Migration Fixes | Prod-migration | Both | All |  |  |  |  | Mandatory | Atlassian
| Update links in Confluence to point to new Confluence address | Prod-migration | Confluence | All |  |  |  |  | Mandatory | Atlassian
| Update links in Confluence to point to new Jira address | Prod-migration | Confluence | All |  |  |  |  | Mandatory | Atlassian
| Update links in Jira to point to new Jira address | Prod-migration | Jira | All |  |  |  |  | Mandatory | Atlassian
| Update links in Jira to point to new Confluence address | Prod-migration | Jira | All |  |  |  |  | Mandatory | Atlassian
| Run Jira Macro Repair | Prod-migration | Confluence | All |  |  |  |  | Mandatory | Customer
| Check Anonymous Access in Cloud | Prod-migration | Jira | All |  |  |  |  | Recommended | Atlassian/Customer |  | Link to documentation
| Check Anonymous Access in Cloud | Prod-migration | Confluence | All |  |  |  |  | Recommended | Atlassian/Customer |  | Link to documentation
| Update projects with project avatars | Prod-migration | Jira | Site Import |  |  |  |  | Recommended | Atlassian
| Complete the UAT | Prod-migration | Both | All |  |  |  |  | Recommended | Customer
| Decision point: Go/No go | Prod-migration | Both | All |  |  |  |  | Mandatory | Customer
| Check-in with Atlassian | Prod-migration | Both | All |  |  |  |  | Mandatory | Customer
ROLLBACK PLAN
| Update announcement banner stating migration is a No-Go and remove read-only | Rollback plan | Jira | All |  |  |  |  | Recommended | Customer |  | Link to documentation
| Update announcement banner stating migration is a No-Go and remove read-only | Rollback plan | Confluence | All |  |  |  |  | Recommended | Customer |  | Link to documentation
| Remove server from read-only | Rollback plan | Both | All |  |  |  |  | Recommended | Customer
| Remove partially migrated projects in cloud | Rollback plan | Jira | Migration Assitant |  |  |  |  | Conditional | Customer |  | Leave the data if investigation is needed to identify cause of migration failure
| Remove partially migrated spaces in cloud | Rollback plan | Confluence | Migration Assitant |  |  |  |  | Conditional | Customer |  | Leave the data if investigation is needed to identify cause of migration failure
POST-PROD MIGRATION
| Set up SSO | Post-prod migration | Both | All |  |  |  |  | Conditional
| Set up SCIM user provisioning | Post-prod migration | Both | All |  |  |  |  | Conditional
| Triage and fix issues | Post-prod migration | Both | All |  |  |  |  | Conditional
| Check-in with Atlassian | Post-prod migration | Both | All |  |  |  |  | Mandatory

## 🧪UAT test cases
Area | Product | Test case | Subtasks | Priority | Link | Status on testing | Responsible | Comments
ADMINISTRATION
Administration | N/A | Global permissions
Administration | Confluence | Space permissions
Administration | Jira | Project permissions
Administration | Confluence | Product audit log
Administration | Jira | Product audit log
MIGRATION
Migration | Confluence | Attachments | - Same number as in server
Migration | Jira | Attachments | - Same number as in server
Migration | N/A | Users
Migration | N/A | Permissions
Migration | N/A | Groups
Migration | Confluence | Spaces | - Same number as in server
Migration | Confluence | Pages | - Same number as in server
Migration | Jira | Projects | - Same number as in server
Migration | Jira | Issues | - Same number as in server
Migration | Jira | Workflows
Migration | Jira | Boards
CONNECTION
Connection | N/A | Application links
Connection | N/A | Integrations
FUNCTIONALITY
Functionality | Jira | Create a project
Functionality | Jira | Create an issue
Functionality | Jira | Delete a project
Functionality | Jira | Workflows
Functionality | Jira | Issues
Functionality | Confluence | Macros
Functionality | Confluence | Create a space
Functionality | Confluence | Create a page
Functionality | Confluence | Share a page
Functionality | Confluence | Delete a space
Functionality | Confluence | Delete a page
Functionality | Confluence | Archive a page
Functionality | Confluence | Analytics
Functionality | N/A | Log in
Functionality | N/A | End-user access
Functionality | Confluence | Update a page
Functionality | Confluence | Test APP NAME
Functionality | Jira | Test APP NAME
Functionality | Confluence | Change page content formatting
Functionality | Confluence | Comment on a page
Functionality | Confluence | Edit a page using the new editor
Functionality | Confluence | Create Jira issue from highlighted text
Functionality | Confluence | Test MACRO NAME
Functionality | Confluence | Links
Functionality | Confluence | Copy a page
Functionality | Confluence | Move a page
Functionality | Jira | Link a Confluence page to an issue
Functionality | Confluence | Watch a page
Functionality | Confluence | Page history
Functionality | Confluence | User profile
Functionality | Confluence | Export a PDF
Functionality | Jira | Watch an issue
Functionality | N/A | New employee onboarding
Functionality | N/A | Group changes
Functionality | Jira | Transition an issue
APPS
Apps
Apps
Apps

## ☑️ Post-migration checklist
Postcheck | Test migration output | Prod migration output | Delta
JIRA POST-MIGRATION CHECKS
Total number of groups
Total number of users (not Service Desk Customers)
Total number of workflows |  |  | 0
Total number of issues |  |  | 0
Total number of projects |  |  | 0
Total number of attachments |  |  | 0
Total size of attachments per Project |  |  | 0
Total number of statuses |  |  | 0
Total number of issuetypes |  |  | 0
Total number of resolutions |  |  | 0
Total number of issue type schemes |  |  | 0
Total number of field configuration |  |  | 0
Total number of field configuration schemes |  |  | 0
Total number of custom fields |  |  | 0
Total number of screens |  |  | 0
Total number of screen schemes |  |  | 0
Total number of workflow schemes |  |  | 0
Total number of permission schemes |  |  | 0
Total number of issue security schemes |  |  | 0
Total number of issue security level |  |  | 0
Total number of notification schemes |  |  | 0
Total number of dashboards |  |  | 0
Check for assignees of issues that are not present in the CWD Table |  |  | 0
Check for reporters of issues that are not present in the CWD User Table |  |  | 0
Check for any missing project leads that may have an entry in the app_user table but not present in the IDP directory |  |  | 0
Check for any missing comment author that may have an entry in the app_user table but not present in the IDP directory |  |  | 0
Filters shared with ‘Group (Anyone)’ |  |  | 0
Dashboards shared with ‘Group (Anyone)’ |  |  | 0
Agile boards shared with ‘Group (Anyone)’ |  |  | 0
Check for Post-functions not native to the Cloud in the migrated workflows. (Add-ons and apps etc) |  |  | 0
Check for Validators not native to the Cloud in the migrated workflows. (Add-ons and apps etc) |  |  | 0
Check for Conditions not native to the Cloud in the migrated workflows. (Add-ons and apps etc) |  |  | 0
CONFLUENCE POST-MIGRATION CHECKS
Total number of spaces |  |  | 0
Total size of attachments |  |  | 0
Total size of attachments per space |  |  | 0
List of attachments per page on a space |  |  | 0
List of attachments on a page |  |  | 0
List of broken attachments |  |  | 0

## C2C Pre-migration checklist
| Priority | Status | Responsible | Comments
MIGRATION METHOD: CONFLUENCE CLOUD SITE IMPORT
Confirm destination site does not have a Jira product | Mandatory |  | Customer
Confirm your migration method | Mandatory |  | Customer
Confirm your user migration plan | Mandatory |  | Customer | https://support.atlassian.com/migration/docs/determine-your-user-migration-strategy/#Confluence-user-migration-strategies
Confirm data size of the backup and XML file | Mandatory |  | Customer
Ensure you have the right permissions | Mandatory |  | Customer | https://support.atlassian.com/confluence-cloud/docs/get-started-as-confluence-cloud-administrator/
Contact app vendors for app data migration | Mandatory |  | Customer
Determine custom templates recreation plan | Mandatory |  | Customer | https://support.atlassian.com/confluence-cloud/docs/create-a-template/
Back up your cloud site | Mandatory |  | Customer | https://support.atlassian.com/confluence-cloud/docs/create-a-site-backup/#Createasitebackup-Backup-export-yourConfluenceinstance
Run a test migration | Mandatory |  | Customer | We strongly encourage performing a dry-run of the import and doing User Acceptance Testing on a test cloud site (which can be created using a free trial) before proceeding with the import on your production cloud site.
Notify support of your migration plan | Mandatory |  | Customer | If you’ll be performing your migration over a weekend or holiday, or are migrating over 1,000 users to cloud, get in touch at least two weeks in advance to let us know. This is so we can ensure we have extra support on hand during your migration.
MIGRATION METHOD: CONFLUENCE CLOUD SPACE BY SPACE (XML) IMPORT
Check destination site does not have the same space key | Mandatory |  | Customer | https://confluence.atlassian.com/confkb/how-to-copy-or-rename-a-space-in-confluence-169578.html
Confirm your migration method | Mandatory |  | Customer
Create a user migration plan | Mandatory |  | Customer | https://support.atlassian.com/confluence-cloud/docs/import-a-confluence-cloud-space/#ImportaConfluenceCloudspacetoanexistingcloudsite-Notesaboutthespaceimport
Ensure you have the right permissions | Mandatory |  | Customer | https://support.atlassian.com/confluence-cloud/docs/get-started-as-confluence-cloud-administrator/
Contact app vendors for app data migration | Mandatory |  | Customer
Confirm if your destination site also has Jira for linking spaces to projects during import | Recommended |  | Customer
Run a test migration | Mandatory |  | Customer | We strongly encourage performing a dry-run of the import and doing User Acceptance Testing on a test cloud site (which can be created using a free trial) before proceeding with the import on your production cloud site.
Notify support of your migration plan | Mandatory |  | Customer | If you’ll be performing your migration over a weekend or holiday, or are migrating over 1,000 users to cloud, get in touch at least two weeks in advance to let us know. This is so we can ensure we have extra support on hand during your migration.
MIGRATION METHOD: IMPORT TO CONFLUENCE DATA CENTER AND MIGRATE VIA CCMA
Confirm your migration method | Mandatory |  | Customer
Create a user migration plan | Mandatory |  | Customer
Ensure you have Data Center setup knowledge | Mandatory |  | Customer | https://confluence.atlassian.com/doc/installing-confluence-183468566.html
Ensure you have the right permissions | Mandatory |  | Customer
Contact app vendors for app data migration | Mandatory |  | Customer
Run a test migration | Mandatory |  | Customer | We strongly encourage performing a dry-run of the import and doing User Acceptance Testing on a test cloud site (which can be created using a free trial) before proceeding with the import on your production cloud site.
Notify support of your migration plan | Mandatory |  | Customer | If you’ll be performing your migration over a weekend or holiday, or are migrating over 1,000 users to cloud, get in touch at least two weeks in advance to let us know. This is so we can ensure we have extra support on hand during your migration.
MIGRATION METHOD: JIRA CLOUD TO CLOUD MIGRATION ASSISTANT
Check Admin Permissions | Mandatory |  | Customer | https://support.atlassian.com/migration/docs/prepare-sites-for-a-cloud-to-cloud-migration/
Confirm source and destination site host the same products | Mandatory |  | Customer
Install same source apps on destination site | Mandatory |  | Customer
Confirm with app vendor data can be migrated | Mandatory |  | Customer
Check user limts | Mandatory |  | Customer
Check for any existing projects | Mandatory |  | Customer | https://support.atlassian.com/migration/docs/perform-a-cloud-to-cloud-migration-for-jira/
Review project permissions | Mandatory |  | Customer
Review what gets migrated documentation | Recommended |  | Customer | https://support.atlassian.com/migration/docs/what-migrates-in-a-cloud-to-cloud-migration-for-jira/
Ensure Jira Service Management isn't in scope for all Jira methods except merge in DC/Server | Mandatory |  | Customer | https://support.atlassian.com/migration/docs/what-migrates-in-a-cloud-to-cloud-migration-for-jira/#What-isn%E2%80%99t-migrated
Convert any team-managed projects into company managed | Mandatory |  | Customer | https://support.atlassian.com/jira-software-cloud/docs/migrate-between-team-managed-and-company-managed-projects/#Things-to-keep-in-mind-if-you-migrate-from-team-managed-to-company-managed
Check projects aren’t available to the public, unless explicitly allowed anonymous or public access | Mandatory |  | Customer
Manually add users to groups | Mandatory |  | Customer
Run a test migration | Mandatory |  | Customer | We strongly encourage performing a dry-run of the import and doing User Acceptance Testing on a test cloud site (which can be created using a free trial) before proceeding with the import on your production cloud site.
Notify support of your migration plan | Mandatory |  | Customer | If you’ll be performing your migration over a weekend or holiday, or are migrating over 1,000 users to cloud, get in touch at least two weeks in advance to let us know. This is so we can ensure we have extra support on hand during your migration.
MIGRATION METHOD: IMPORT TO JIRA DATA CENTER AND MIGRATE VIA JCMA
Install Jira Data Center | Mandatory |  | Customer | https://confluence.atlassian.com/jirakb/merge-multiple-jira-cloud-sites-779160767.html
Convert any team-managed projects into company managed | Mandatory |  | Customer | https://support.atlassian.com/jira-software-cloud/docs/migrate-between-team-managed-and-company-managed-projects/#Things-to-keep-in-mind-if-you-migrate-from-team-managed-to-company-managed
Contact vendor to migrate app data | Mandatory |  | Customer
Create a backup of source cloud site | Mandatory |  | Customer | https://support.atlassian.com/jira-cloud-administration/docs/export-issues/
Import Data from source cloud site to Data Center | Mandatory |  | Customer | https://confluence.atlassian.com/adminjiracloud/migrating-from-jira-cloud-to-server-776636236.html
Use JCMA to migrate into destination cloud site | Mandatory |  | Customer | https://confluence.atlassian.com/cloud/use-the-jira-cloud-migration-assistant-to-migrate-993925215.html
Run a test migration | Mandatory |  | Customer | We strongly encourage performing a dry-run of the import and doing User Acceptance Testing on a test cloud site (which can be created using a free trial) before proceeding with the import on your production cloud site.
Notify Support of your migration plan | Mandatory |  | Customer | If you’ll be performing your migration over a weekend or holiday, or are migrating over 1,000 users to cloud, get in touch at least two weeks in advance to let us know. This is so we can ensure we have extra support on hand during your migration.
MIGRATION METHOD: USE CSV FILE TO IMPORT ISSUES
Search for issues in the required projects from your source site | Mandatory |  | Customer
Export issues from source site as a CSV file | Mandatory |  | Customer | https://support.atlassian.com/jira-work-management/docs/work-with-search-results/
Create projects as empty in destination site | Mandatory |  | Customer
Set up the project configurations | Mandatory |  | Customer
Import CSV file into destination site | Mandatory |  | Customer | https://support.atlassian.com/jira-cloud-administration/docs/import-data-from-a-csv-file/
Import attachments into Cloud site | Recommended |  | Customer | https://confluence.atlassian.com/cloudkb/importing-attachments-into-jira-cloud-using-csv-external-system-importer-966669960.html

## 📖C2C Migration runbook
Task | Timeline | Responsible | Product | Method | Date | Start time | Duration (minutes) | End time | Priority | Status | Notes
PRE-TEST MIGRATION
Develop UAT plan | Pre-test migration | Customer | Both | All |  |  |  |  | Mandatory |  | Customer to start creating UAT logistics (e.g. who, when, how)
Send UAT plan to UAT users | Pre-test migration | Customer | Both | All |  |  |  |  | Mandatory |  | Customer to notify users of the plan to perform UAT
Confirm access to both source and destination cloud sites as an organization admin or site admin | Pre-test migration | Customer | Both | All |  |  |  |  | Mandatory
Obtain number of apps on source cloud site | Pre-test migration | Customer | Both | All |  |  |  |  | Mandatory
Install apps on your destination cloud site | Pre-test migration | Customer |  | All |  |  |  |  | Recommended
Determine storage usage on source site | Pre-test migration | Customer | Both | All |  |  |  |  | Recommended |  | https://support.atlassian.com/security-and-access-policies/docs/track-storage-and-move-data-across-products/
Ensure you want exceed your cloud user limit at destination site | Pre-test migration | Customer | Both | All |  |  |  |  | Mandatory
Obtain number of projects | Pre-test migration | Customer | Jira | All Jira Methods |  |  |  |  | Optional |  | https://community.atlassian.com/t5/Jira-questions/Is-there-any-way-to-get-the-count-of-total-projects-in-JIRA/qaq-p/1733210
Obtain number of spaces | Pre-test migration | Customer | Confluence | All Conf Methods |  |  |  |  | Optional
Check for duplicate space keys between source and destination | Pre-test migration | Customer | Confluence | All Conf Methods |  |  |  |  | Mandatory
Convert team managed projects to company managed projects | Pre-test migration | Customer | Jira | All Jira Methods |  |  |  |  | Mandatory |  | https://support.atlassian.com/jira-software-cloud/docs/migrate-between-team-managed-and-company-managed-projects/#Things-to-keep-in-mind-if-you-migrate-from-team-managed-to-company-managed
Audit link requirements to see what needs to be fixed post-production migration | Pre-test migration | Customer | Both | All |  |  |  |  | Mandatory
Ensure there's an app migration strategy defined | Pre-test migration | Customer with Atlassian | Both | All |  |  |  |  | Recommended |  | Link to documentation: Develop an app migration strategy, open vendor tickets, etc.
Ensure there's a user migration strategy defined | Pre-test migration | Customer with Atlassian | Both | All |  |  |  |  | Mandatory |  | Link to documentation
Ensure there's an attachment migration strategy defined | Pre-test migration | Customer | Jira | Jira CSV Import |  |  |  |  | Mandatory |  | https://confluence.atlassian.com/cloudkb/importing-attachments-into-jira-cloud-using-csv-external-system-importer-966669960.html
Ensure you understand how migration affects your billing | Pre-test migration | Customer | Both | All |  |  |  |  | Recommended |  | https://support.atlassian.com/migration/docs/prepare-sites-for-a-cloud-to-cloud-migration/#Understand-how-migration-affects-your-billing
Set up a test site | Pre-test migration | Customer | Both | All |  |  |  |  | Mandatory |  | Link to documentation
Complete pre-migration checklist | Pre-test migration | Customer with Atlassian | Both | All |  |  |  |  | Mandatory |  | C2C pre-migration checklist
TEST MIGRATION
Feature Flag Preparation | Test migration | Customer with Atlassian | Jira | Jira Cloud to Cloud |  |  |  |  | Mandatory |  | Customer to check if they have access to the cloud to cloud migration feature. If not request Atlassian support to enable feature flag required for this migration.
Execute user migration strategy | Test migration | Customer | Both | All |  |  |  |  | Mandatory
Migrate Users and Groups/Memberships | Test migration | Customer | Both | All |  |  |  |  | Mandatory
Execute attachment migration strategy | Test migration | Customer | Jira | Jira CSV Import |  |  |  |  | Mandatory |  | https://support.atlassian.com/jira-cloud-administration/docs/import-data-from-a-csv-file/
Perform Migration | Test migration | Customer | Both | All |  |  |  |  | Mandatory
Create the migration plan, choose the destination site and choose the project to migrate | Test migration | Customer | Jira | Jira Cloud to Cloud |  |  |  |  | Mandatory |  | https://support.atlassian.com/migration/docs/perform-a-cloud-to-cloud-migration-for-jira/#2.-Create-a-migration
Stop changes or deletion of entities on source site during migration | Test migration | Customer | Jira | Jira Cloud to Cloud |  |  |  |  | Mandatory
Placeholder - fill in tasks specific to this migration | Test migration | Customer | Both | All |  |  |  |  | Mandatory
Placeholder - fill in tasks specific to this migration | Test migration | Customer | Both | All |  |  |  |  | Mandatory
Post-Migration Fixes | Test migration | Atlassian | Both | All |  |  |  |  | Mandatory
Test macros in cloud to identify if there are broken macros | Test migration | Customer | Confluence | Conf Space Import |  |  |  |  | Mandatory |  | If there are broken macros, work with support to see if there are ways to resolve it. If the macro is from a third party app, will need to work with vendor to check for resolution
Run Jira Macro Repair | Test migration | Customer | Confluence | Conf Space Import |  |  |  |  | Recommended |  | https://confluence.atlassian.com/confkb/using-the-jira-macro-repair-1084362152.html
Check Anonymous Access in Cloud | Test migration | Customer | Both | All |  |  |  |  | Recommended
Send communication to start UAT | Test migration | Customer | Both | All |  |  |  |  | Recommended |  | Make sure to test all portions of the application
PRE-PROD MIGRATION
Touchpoint with Atlassian: review runbook | Pre-prod migration | Customer with Atlassian | Both | All |  |  |  |  | Mandatory
Ensure prod site has an extended trial/license applied | Pre-prod migration | Customer | Both | All |  |  |  |  | Mandatory
If cutover date available, ensure end users are alerted ahead of time of migration | Pre-prod migration | Customer | Both | All |  |  |  |  | Mandatory
Develop post-migration support plan for admins and users | Pre-prod migration | Customer | Both | All |  |  |  |  | Recommended |  | Customer to discuss internally on the support logistics
Complete pre-migration checklist | Pre-prod migration | Customer | Jira | All |  |  |  |  | Mandatory |  | C2C pre-migration checklist
Complete pre-migration checklist | Pre-prod migration | Customer | Confluence | All |  |  |  |  | Mandatory |  | C2C pre-migration checklist
Review UAT plan | Pre-prod migration | Customer | Both | All |  |  |  |  | Mandatory
Send UAT plan to UAT users | Pre-prod migration | Customer | Both | All |  |  |  |  | Mandatory
Confirm Go/No-Go with Atlassian 10 business days prior to Prod migration | Pre-prod migration | Customer | Both | All |  |  |  |  | Mandatory
Add announcement banner outlining changes are coming | Pre-prod migration | Customer | Jira | All |  |  |  |  | Recommended |  | https://community.atlassian.com/t5/Jira-articles/Admins-notify-your-Jira-instance-of-system-wide-changes-with-the/ba-p/1841132
Add announcement banner outlining changes are coming | Pre-prod migration | Customer | Confluence | All |  |  |  |  | Recommended |  | Use the following workaround: https://community.atlassian.com/t5/Confluence-questions/Add-Site-Banner-in-Confluence-Cloud/qaq-p/1654323
Migrate Users and Groups/Memberships | Pre-prod migration | Customer | Both | All |  |  |  |  | Recommended |  | Recommended to get a CSV export a day before production run: https://support.atlassian.com/organization-administration/docs/export-users-from-a-site/
Update announcement banner stating when the site will be migrating | Pre-prod migration | Customer | Jira | All |  |  |  |  | Mandatory
Update announcement banner stating when site will be migrating | Pre-prod migration | Customer | Confluence | All |  |  |  |  | Mandatory
PROD MIGRATION
Update browse project permission scheme / create and edit issues permission scheme | Prod-migration | Customer | Jira | All Jira Methods |  |  |  |  | Recommended |  | https://community.atlassian.com/t5/Jira-Software-questions/Create-Read-Only-Users/qaq-p/1459889
Update space permissions and remove Add permission | Prod-migration | Customer | Confluence | All Conf Methods |  |  |  |  | Recommended |  | https://confluence.atlassian.com/doc/space-permissions-overview-139521.html
Update announcement banner stating site is now read-only | Prod-migration | Customer | Jira | All |  |  |  |  | Recommended
Update announcement banner stating site is now read-only | Prod-migration | Customer | Confluence | All |  |  |  |  | Recommended
Perform Migration | Prod-migration | Customer | Both | All |  |  |  |  | Mandatory
Placeholder - fill in tasks specific to this migration | Prod-migration |  | Both | All
Placeholder - fill in tasks specific to this migration | Prod-migration |  | Both | All
POST-PROD MIGRATION
Triage and fix issues | Post-prod migration | Atlassian/Customer | Both | All |  |  |  |  | Conditional
Validate your Marketplace app data has migrated | Post-prod migration | Customer | Both | All |  |  |  |  | Recommended
Import any attachments | Post-prod migration | Customer | Jira | Jira CSV Import |  |  |  |  | Recommended
Run Jira Macro Repair | Post-Prod-migration | Customer | Confluence | All Conf Methods |  |  |  |  | Mandatory
Check Anonymous Access in Cloud | Post-Prod-migration | Customer | Jira | All |  |  |  |  | Recommended
Check Anonymous Access in Cloud | Post-Prod-migration | Customer | Confluence | All |  |  |  |  | Recommended
Complete the UAT | Post-Prod-migration | Customer | Both | All |  |  |  |  | Recommended
Re-install any compatible apps, like Questions for Confluence and Team Calendars for Confluence | Post-Prod-migration | Customer | Confluence | All Conf Methods |  |  |  |  | Recommended |  | https://confluence.atlassian.com/teamcal/export-team-calendars-content-to-other-calendars-240913738.html
Check Confluence space shortcuts | Post-Prod-migration | Customer | Confluence | All Conf Methods |  |  |  |  | Recommended |  | https://support.atlassian.com/confluence-cloud/docs/configure-shortcut-links/
Recreate custom templates | Post-Prod-migration | Customer | Confluence | All Conf Methods |  |  |  |  | Recommended |  | https://confluence.atlassian.com/doc/create-a-template-296093779.html
Add users to groups | Post-Prod-migration | Customer | Jira | Jira Cloud to Cloud |  |  |  |  | Mandatory
Update links in Confluence | Post-Prod-migration | Atlassian | Confluence | All |  | Typically started the Monday after Production migration |  |  | Mandatory |  | Notify Atlassian support to assist with link fixing
Update links in Jira | Post-Prod-migration | Atlassian | Jira | All |  | Typically started the Monday after Production migration |  |  | Mandatory |  | Notify Atlassian support to assist with link fixing
ROLLBACK
Update announcement banner stating migration is a No-Go and remove read-only | Rollback plan | Customer | Jira | All |  |  |  |  | Recommended
Update announcement banner stating migration is a No-Go and remove read-only | Rollback plan | Customer | Confluence | All |  |  |  |  | Recommended
Update browse project permission scheme / create and edit issues permission scheme | Rollback plan | Customer | Jira | All |  |  |  |  | Recommended
Update space permissions and remove Add permission | Rollback plan | Customer | Confluence | All |  |  |  |  | Recommended
Remove partially migrated projects in cloud | Rollback plan | Customer | Jira | All |  |  |  |  | Conditional |  | https://support.atlassian.com/jira-cloud-administration/docs/delete-a-project/ Leave the data if investigation is needed to identify cause of migration failure
Remove partially migrated spaces in cloud | Rollback plan | Customer | Confluence | All |  |  |  |  | Conditional |  | https://support.atlassian.com/confluence-cloud/docs/delete-a-space/ Leave the data if investigation is needed to identify cause of migration failure
Restore cloud site from a backup | Rollback plan | Customer | Jira | All Jira Methods |  |  |  |  | Conditional |  | This is a consideration if the migration was a merge to destination site and a backup was taken prior to mgiration